## Scheduled for Shift
Work Order | Equipment | Description | 1 - WO Owner | PM Compliance Max
77433262 | MOD.002 | SOFTLINES MOD LANE 2 DAILY | ADCOURTR | 2022-11-17
77424496 | MOD.002 | SOFTLINES MOD LANE 1 STROBE BACK HALF | ADCOURTR | 2022-11-18
77424501 | MOD.002 | SOFTLINES MOD LANE 2 STROBE BACK HALF | ADCOURTR | 2022-11-18
77705277 | 1018500055 | DEMATIC MODEL 9405 13 WEEK PM | ADCOURTR | 2022-12-03
77433259 | MOD.002 | SOFTLINES MOD LANE 1 DAILY | ADCOURTR | 2022-11-17
77432744 | RCV.056 | SOFTLINES RECEIVE LANES DAILY | AZJSER | 2022-11-17
77432735 | RTE.025 | ROUTING SORTER INDUCT AND RECIRC DAILY | AZJSER | 2022-11-17
77432725 | RTE.025 | SOFTLINES ROUTING LINES DAILY | AZJSER | 2022-11-17
77478774 | 1013108055 | DEMATIC 2430 - SL2 DAILY CHECK | AZJSER | 2022-11-17
77504121 | 1013800110 | TRANSNORM TS1500-140 V2-030 4 WEEK | CODREICH | 2022-11-22
77433334 | DEPT.TSHIP | SOFTLINES TRANSHIP DAILY | CODREICH | 2022-11-17
77478771 | 1018300030 | DEMATIC 2430 - SL2 DAILY CHECK | CODREICH | 2022-11-17
77433615 | 101087857 | KOMAR EM40-GHS 01 DAY PM | CODREICH | 2022-11-17
77433613 | 101087856 | KOMAR EM40-GHS 01 DAY PM | CODREICH | 2022-11-17
77432755 | SHP.056 | SOFTLINES SHIP LANES 2 OF 2 DAILY | DEVERDAN | 2022-11-17
77433598 | 1013850110 | INTRALOX DARB S4500 DAILY | DEVERDAN | 2022-11-17
77432767 | SHP.056 | SOFTLINES SHIP LOOP 2 OF 2 DAILY | DEVERDAN | 2022-11-17
77433593 | 1013850070 | INTRALOX DARB S4500 DAILY | DEVERDAN | 2022-11-17
77433596 | 1013850090 | INTRALOX DARB S4500 DAILY | DEVERDAN | 2022-11-17
77433600 | 1013850130 | INTRALOX DARB S4500 DAILY | DEVERDAN | 2022-11-17
77433604 | 1013850610 | INTRALOX DARB S4500 DAILY | DEVERDAN | 2022-11-17
77433605 | 1013850630 | INTRALOX DARB S4500 DAILY | DEVERDAN | 2022-11-17
77433602 | 1013850590 | INTRALOX DARB S4500 DAILY | DEVERDAN | 2022-11-17
77399417 | AR.BOT.HDU.X16N-N-2035-002510 | X DRIVE BOT 52 WEEK PM | DGULDIN | 2022-12-15
77399422 | AR.BOT.HDU.X16N-N-2035-002508 | X DRIVE BOT 52 WEEK PM | DGULDIN | 2022-12-15
77401430 | AR.BOT.HDU.X16N-N-2035-002506 | X DRIVE BOT 26 WEEK PM | DGULDIN | 2022-12-05
77480010 | AR | REPEAT OFFENDER CHECK DAILY | DGULDIN | 2022-11-17
77401433 | AR.BOT.HDU.X16N-N-2035-002507 | X DRIVE BOT 26 WEEK PM | DGULDIN | 2022-12-05
75748442 | 1013850020 | *Kitted* clicking sound emanating from output bearing of gearbox | DGULDIN | 2022-11-05
77424242 | BLDG.DOCK | BBM - WEEKLY DOCK FAN INSP / CLEAN | HANEJAM | 2022-11-18
77424227 | B.ENCLOSURE.243 | BBM - WEEKLY EXTERIOR SYSTEM CHECK | HANEJAM | 2022-11-18
77424490 | MOD.002 | SOFTLINES MOD LANE 4 STROBE BACK HALF | LMDURHAM | 2022-11-18
77504124 | 1013800530 | TRANSNORM TS1500-140 V2-030 4 WEEK | LMDURHAM | 2022-11-22
77504127 | 1013800590 | TRANSNORM TS1500-140 V2-030 4 WEEK | LMDURHAM | 2022-11-22
77433228 | MOD.002 | SOFTLINES MOD LANE 3 DAILY | LMDURHAM | 2022-11-17
77433254 | MOD.002 | SOFTLINES MOD LANE 4 DAILY | LMDURHAM | 2022-11-17
77424505 | MOD.002 | SOFTLINES MOD LANE 3 STROBE BACK HALF | LMDURHAM | 2022-11-18
77433611 | 101087813 | JR AUTOMATION RWC4 V-5 DAILY PM | MLLERHB | 2022-11-17
77433609 | 101087854 | LANTECH Q300XT DAILY PM TASK | MLLERHB | 2022-11-17
77433607 | 101087849 | LANTECH Q300XT DAILY PM TASK | MLLERHB | 2022-11-17
77423948 | 101087813 | JR AUTOMATION RWC4 V-5 WEEKLY PM | MLLERHB | 2022-11-18
78165163 | 1013850530 | drive pulleys missaligned bed number 1018850530 | MOTRONIM | 2022-12-30
77779736 | 10SL0712 | DEMATIC SEMI-AUTO INDUCT BELT 13 WEEK | MUBARRET | 2022-12-05
77433313 | RDG1.SLAM.03 | SLAM DAILY SYSTEM CHECK | NUTTERGN | 2022-11-17
77432720 | RDG1.SLAM.06 | SLAM DAILY SYSTEM CHECK | NUTTERGN | 2022-11-17
77432721 | RDG1.SLAM.07 | SLAM DAILY SYSTEM CHECK | NUTTERGN | 2022-11-17
77433311 | RDG1.SLAM.02 | SLAM DAILY SYSTEM CHECK | NUTTERGN | 2022-11-17
77433309 | RDG1.SLAM.01 | SLAM DAILY SYSTEM CHECK | NUTTERGN | 2022-11-17
77424830 | RDG1.SLAM.05 | SLAM WEEKLY | NUTTERGN | 2022-11-18
77433315 | RDG1.SLAM.04 | SLAM DAILY SYSTEM CHECK | NUTTERGN | 2022-11-17
77433589 | 1013800560 | INTRALOX DARB S4500 DAILY | ORZMIGUE | 2022-11-17
77433587 | 1013800540 | INTRALOX DARB S4500 DAILY | ORZMIGUE | 2022-11-17
77433585 | 1013800160 | INTRALOX DARB S4500 DAILY | ORZMIGUE | 2022-11-17
77432752 | SHP.056 | SOFTLINES SHIP LANES 1 OF 2 DAILY | ORZMIGUE | 2022-11-17
77478783 | 1013800045 | INTRALOX DARB S4500 DAILY | ORZMIGUE | 2022-11-17
77478787 | 1013800120 | INTRALOX DARB S4500 DAILY | ORZMIGUE | 2022-11-17
77433583 | 1013800140 | INTRALOX DARB S4500 DAILY | ORZMIGUE | 2022-11-17
77433591 | 1013800580 | INTRALOX DARB S4500 DAILY | ORZMIGUE | 2022-11-17
77432774 | SHP.056 | SOFTLINES SHIP LOOP 1 OF 2 DAILY | ORZMIGUE | 2022-11-17
77424142 | BLDG.RESTROOM | RESTROOM INSPECTION (BACK HALF) | PENAEFRY | 2022-11-18
77659999 | 1018221095 | DEMATIC MODEL 9410 13 WEEK PM | TROUGHTI | 2022-12-02
77433294 | PCK.044 | SOFTLINES PACK LANE 7 DAILY | WANSEDAV | 2022-11-17
77433289 | PCK.044 | SOFTLINES PACK LANE 4 DAILY | WANSEDAV | 2022-11-17
77433274 | PCK.044 | SOFTLINES PACK LANE 3 DAILY | WHTLE | 2022-11-17
77433223 | PCK.044 | SOFTLINES PACK LANE 1 DAILY | WHTLE | 2022-11-17
77433225 | PCK.044 | SOFTLINES PACK LANE 5 DAILY | WHTLE | 2022-11-17
77433277 | PCK.044 | SOFTLINES PACK LANE 6 DAILY | WHTLE | 2022-11-17
77433270 | PCK.044 | SOFTLINES PACK LANE 2 DAILY | WHTLE | 2022-11-17
77433297 | PCK.044 | SOFTLINES PACK LANE 8 DAILY | ZSINGER | 2022-11-17
77433206 | PCK.044 | SOFTLINES PACK LANE 14 DAILY | ZSINGER | 2022-11-17
77433209 | PCK.044 | SOFTLINES PACK LANE 12 DAILY | ZSINGER | 2022-11-17
77433213 | PCK.044 | SOFTLINES PACK LANE 13 DAILY | ZSINGER | 2022-11-17
77433219 | PCK.044 | SOFTLINES PACK LANE 11 DAILY | ZSINGER | 2022-11-17
77433280 | PCK.044 | SOFTLINES PACK LANE 9 DAILY | ZSINGER | 2022-11-17
77433284 | PCK.044 | SOFTLINES PACK LANE 10 DAILY | ZSINGER | 2022-11-17

## Backlog
Work Order | Equipment | Description | 1 - WO Owner | Type | Sched. Start Date | PM Compliance Max | Reported By
78902010 | 1013850530 | intermittent screeching from drive area | WHTLE | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-11-16 | 2022-12-07 | ADCOURTR
78900107 | 1013850630 | jams on ship loop | FICERIC | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-11-16 | 2023-01-15 | FICERIC
78894524 | REMEDY.RME-EQP | OB MRS |  | Breakdown - Equipment is Not Running | 2022-11-16 | 2023-01-15
78891883 | 1018500055 | pin replacement/clicking snubber (Charge end) | ADCOURTR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-16 | 2023-01-15 | ADCOURTR
78886970 | 1018221070 | AR FLOOR CHUTE LUBRICATION | MOTRONIM | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-16 | 2023-01-15 | MOTRONIM
78879120 | 1013800120 | RDG1 - 0 - U800120_FMD(Outbound northwest intralox 1, EAM Asset: 1013800120) fla |  | Condition Based Monitoring | 2022-11-16 | 2022-11-16
78879119 | 1013800000 | RDG1 - 0 - U800000_FMD(Slam Package Takeaway for North Loop, EAM Asset: 10138000 |  | Condition Based Monitoring | 2022-11-16 | 2022-11-16
78879118 | 1013800140 | RDG1 - 0 - U800140_FMD(Outbound northwest intralox 2, EAM Asset: 1013800140) fla |  | Condition Based Monitoring | 2022-11-16 | 2022-11-16
78879113 | 1013800160 | RDG1 - 0 - U800160_FMD(Outbound northwest intralox 3, EAM Asset: 1013800160) fla |  | Condition Based Monitoring | 2022-11-16 | 2022-11-16
78879110 | 1013800020 | RDG1 - 0 - U800020_FMD(Bulk distribution conveyor to Outbound North sorter, EAM |  | Condition Based Monitoring | 2022-11-16 | 2022-11-16
78878876 | RDG1.SLAM.06 | Monitor SLAMs | MLLERHB | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-16 | 2023-01-15 | MLLERHB
78878417 | 1013850610 | RDG1 - 0 - U850610_FMD(Outbound southwest intralox 2, EAM Asset: 1013850610) fla |  | Condition Based Monitoring | 2022-11-16 | 2022-11-16
78878177 | 101087814 | [RDG1] RWC4 Down |  | Breakdown - Equipment is Not Running | 2022-11-16 | 2023-01-15
78874666 | GNRL.CONV.CHUTE | Disassembly of Chutes | ZSINGER | Project - Work beyond normal Repair & Maint. | 2022-11-16 | 2022-12-07 | ZSINGER
78869743 | 1018300030 | V groove wheel replacement | BOARDERR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-16 | 2023-01-15 | DGULDIN
78849394 | BLDG.ROOF | leaks | HANEJAM | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-11-15 | 2023-01-14 | ADCOURTR
78828873 | D.LIGHT.INT.242 | Lights Flickering | HANEJAM | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-11-16 | 2023-01-14
78828390 | PSC.2315 | PSC 2319 faulting | KARCHERC | Project - Work beyond normal Repair & Maint. | 2022-11-15 | 2023-01-14 | KARCHERC
78825662 | C.GUARDRAIL.242 | [RDG1]Please inspect and repair column strut by IB | HANEJAM | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-11-16 | 2023-01-14
78821996 | 1018300050 | 'kitted' BROKEN FINGER GUARDS | KUPETZTJ | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-15 | 2023-01-14 | KRISHBTY
78821854 | 1018300045 | 'ordered' BROKEN FINGER GUARD | BOARDERR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-15 | 2023-01-14 | KRISHBTY
78810339 | 1018500350 | 'ordered' end roller shaft/bearing completely worn out | BOARDERR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-15 | 2022-11-16 | WANSEDAV
78791553 | 1018233135 | RDG1 - 0 - U233135_FMD(RTE.SHOE.1; INFEED 02; SLIDER BED CONV; 233135;, EAM Asse | JERNUTTE | Condition Based Monitoring | 2022-11-15 | 2022-11-15
78782195 | 1018300090 | RDG1 - 0 - U300090_FMD(RTE.SHOE.1; REINDUCT (01); SLIDER BED CONV; 300090;, EAM | JERNUTTE | Condition Based Monitoring | 2022-11-15 | 2022-11-14
78782192 | 1018223115 | RDG1 - 0 - U223115_FMD(RTE.SHOE.1; INFEED 04; SLIDER BED CONV; 223115;, EAM Asse | JERNUTTE | Condition Based Monitoring | 2022-11-15 | 2022-11-14
78782191 | 1018221115 | RDG1 - 0 - U221115_FMD(RTE.SHOE.1; INFEED 05; SLIDER BED CONV; 221115;, EAM Asse | JERNUTTE | Condition Based Monitoring | 2022-11-15 | 2022-11-14
78782184 | 1018231130 | RDG1 - 0 - U231130_FMD(RTE.SHOE.1; INFEED 03; SLIDER BED CONV; 231130; (Local_De | JERNUTTE | Condition Based Monitoring | 2022-11-15 | 2022-11-14
78780775 | MOD.L.015 | RDG1 - Remove & reinstall garbage can brackets in mods |  | Project - Work beyond normal Repair & Maint. | 2022-11-14 | 2023-01-13
78729723 | 10SL0312 | Slam 3 Strip Belt Worn/missing/damaged belts | BENJACOH | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-16 | 2023-01-12 | BENJACOH
78728537 | DEPT.HR057 | clouds and air plane project | KRISHBTY | Project - Work beyond normal Repair & Maint. | 2022-11-14 | 2023-01-12
78727464 | 1013500436 | Belt L on 500436 in need of replacement | ERNSW | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-14 | 2023-01-12 | NHUBJERE
78727408 | 1013500435 | 'kitted' Multiple belts found in need of replacement | KUPETZTJ | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-16 | 2023-01-12 | NHUBJERE
78716068 | DEPT.HR057 | BALLOON HANGING NORTH ENTERANCE. SEE PICTURES. | MOTRONIM | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-11-12 | 2023-01-11 | MOTRONIM
78667627 | 1018108045 | 'ordered' Growling coming from the bearing of the drive drum | BOARDERR | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-11-12 | 2023-01-11 | NHUBJERE
78662779 | PCK.044 | Installing New Signage | KRISHBTY | Project - Work beyond normal Repair & Maint. | 2022-11-11 | 2023-01-10
78629683 | 1013800560 | oil leak gear box | TROUGHTI | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-11 | 2023-01-10 | TROUGHTI
78629067 | 1013800000 | belt hoping looks like damaged pully is the cause | SAMBADRA | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-11 | 2023-01-10 | TROUGHTI
78628855 | 1013800020 | light oil leak | TROUGHTI | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-11 | 2023-01-10 | TROUGHTI
78584514 | 1018600015 | PIN IS RUSTY ON SLAVE BED. THE LACING IS ETCHING IN TO IT. | TROUGHTI | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-12 | 2023-01-08 | MOTRONIM
78582855 | 1018500835 | lacing is sticking upward on bed F on 500835 | SAMBADRA | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-16 | 2023-01-08 | MOTRONIM
78565820 | BLDG.HVAC | BMS Alarm - RTU_10 serving [3rd Floor Vending-East] zoneTemp | HANEJAM | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-11-10 | 2022-11-30
78564542 | G.SITE.TRUCKYARD.241 | spill kit shed | HANEJAM | Project - Work beyond normal Repair & Maint. | 2022-11-10 | 2023-01-08
78551678 | PCK.044 | Railing issue with New Pack Tables. | MATHEAST | Project - Work beyond normal Repair & Maint. | 2022-11-09 | 2023-01-08
78549830 | 1018890130 | gearbox hanging from incline is 133 degrees. | KUPETZTJ | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-08 | 2023-01-07 | WANSEDAV
78516468 | 1018108000 | 'ordered' SHAFT FAILING | BOARDERR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-08 | 2023-01-07 | KRISHBTY
78457862 | G.SITE.TRUCKYARD.241 | [RDG1]Please install 6' bench in Driver's Cage IB | HANEJAM | Project - Work beyond normal Repair & Maint. | 2022-11-07 | 2022-11-28
78456221 | AR.BOT.HDU.X16N-N-2035-002350 | DU not booting correctly | KARCHERC | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-11-07 | 2023-01-06 | KARCHERC
78454994 | 1018430000 | 'ordered' REPLACE ROLLERS | BOARDERR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-07 | 2023-01-06 | KRISHBTY
78385382 | CNTRL.080 | Spare Compact logix PLC processor firmware update | PTHR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-14 | 2023-01-04 | PTHR
78375936 | 1018500835 | 'ordered' bad roller on bed E. Marked with an "X". | TONYBENZ | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-14 | 2023-01-03 | MOTRONIM
78354508 | BLDG.DOCK | Finish Dock door quarterly PM | HANEJAM | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-14 | 2023-01-03 | HANEJAM
78342267 | 1018500765 | 'ordered' Bad discharge end roller. BED E | BOARDERR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-10 | 2023-01-03 | MOTRONIM
78305748 | AUDIT | *ordered* PCA-NBS PB 1063 Retrofit | BOARDERR | PCA Work Order | 2022-11-03 | 2023-05-01
78304930 | BLDG.250 | [RDG1] Need to patch & paint walls throughout building. | HANEJAM | Project - Work beyond normal Repair & Maint. | 2022-11-03 | 2023-01-02
78240622 | PSC.2320 | AMZN/RDG1/slKivaA02 PSC 111 (2319) detected failures in the last 24 hours. | AZJSER | Project - Work beyond normal Repair & Maint. | 2022-11-03 | 2022-11-03
78232824 | 1018700000 | 'kitted' v belt has at least one crack and appears to be delaminating | KUPETZTJ | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-01 | 2022-12-31 | WANSEDAV
78212613 | PCK.044 | missing poly bag brackets at pack stations | GENSHART | Project - Work beyond normal Repair & Maint. | 2022-11-01 | 2022-12-31
78204398 | 1018890130 | take up roller making loud clicking noise | BOARDERR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-01 | 2022-12-31 | WANSEDAV
78086654 | DEPT.OB.057 | Bollards need to be installed at DD149 | HANEJAM | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-10-29 | 2022-12-28 | BENJACOH
78015087 | G.SITE.WALLS.241 | Wellness Zone Walls | HANEJAM | Project - Work beyond normal Repair & Maint. | 2022-10-28 | 2022-12-26
77978608 | BLDG.RESTROOM | wax seal leaking | HANEJAM | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-10-28 | 2022-12-26 | LMDURHAM
77964458 | DEPT.OB.057 | Castor wheel replacement | TROUGHTI | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-10-26 | 2022-12-25 | NHUBJERE
77890672 | 1018300030 | ticking noise (see comments) | DGULDIN | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-03 | 2022-12-24 | LMDURHAM
77809012 | PCK.044 | Removal of rail on old pack stations | ERNSW | Project - Work beyond normal Repair & Maint. | 2022-10-23 | 2022-12-22
77705275 | 1013223095 | DEMATIC MODEL 9265 13 WEEK PM | LMDURHAM | PM - Preventative Maintenance | 2022-11-15 | 2022-12-03
77705271 | 1013223090 | DEMATIC MODEL 9190 13 WEEK PM | CODREICH | PM - Preventative Maintenance | 2022-11-15 | 2022-12-03
77705269 | 1013223085 | DEMATIC MODEL 9265 13 WEEK PM | CODREICH | PM - Preventative Maintenance | 2022-11-15 | 2022-12-03
77660021 | 1018223035 | DEMATIC MODEL 9410 13 WEEK PM | WANSEDAV | PM - Preventative Maintenance | 2022-11-15 | 2022-12-02
77660018 | 1018223030 | DEMATIC MODEL 9265 13 WEEK PM | CODREICH | PM - Preventative Maintenance | 2022-11-15 | 2022-12-02
77660007 | 1018223005 | DEMATIC MODEL 9410 13 WEEK PM | LMDURHAM | PM - Preventative Maintenance | 2022-11-15 | 2022-12-02
77660004 | 1018223000 | DEMATIC MODEL 9265 13 WEEK PM | LMDURHAM | PM - Preventative Maintenance | 2022-11-15 | 2022-12-02
77619440 | 1018221070 | DEMATIC MODEL 9265 13 WEEK PM | HILLMROB | PM - Preventative Maintenance | 2022-11-14 | 2022-12-01
77573721 | 1018221015 | DEMATIC MODEL 9410 13 WEEK PM | LMDURHAM | PM - Preventative Maintenance | 2022-11-14 | 2022-11-30
77573718 | 1018221010 | DEMATIC MODEL 9265 13 WEEK PM | LMDURHAM | PM - Preventative Maintenance | 2022-11-14 | 2022-11-30
77525359 | G.SITE.TRUCKYARD.241 | no line between tuck slots | HANEJAM | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-10-17 | 2022-12-15
77504141 | 1018300015 | TRANSNORM TS1500-140 V2-090 4 WEEK | WANSEDAV | PM - Preventative Maintenance | 2022-11-16 | 2022-11-22
77504135 | 1018108025 | TRANSNORM TS1500-140 V2-090 4 WEEK | LMDURHAM | PM - Preventative Maintenance | 2022-11-16 | 2022-11-22
77462285 | 1018214110 | DEMATIC MODEL 9265 13 WEEK PM | ZSINGER | PM - Preventative Maintenance | 2022-11-16 | 2022-11-27
77462282 | 1018214105 | DEMATIC MODEL 9265 13 WEEK PM | ZSINGER | PM - Preventative Maintenance | 2022-11-16 | 2022-11-27
77462280 | 1018214085 | DEMATIC MODEL 2467 13 WEEK PM | ZSINGER | PM - Preventative Maintenance | 2022-11-16 | 2022-11-27
77462277 | 1018214080 | DEMATIC MODEL 9265 13 WEEK PM | NAPONICR | PM - Preventative Maintenance | 2022-11-16 | 2022-11-27
77462276 | 1018214075 | DEMATIC MODEL 9265 13 WEEK PM | NAPONICR | PM - Preventative Maintenance | 2022-11-16 | 2022-11-27
77462274 | 1018214055 | DEMATIC MODEL 2467 13 WEEK PM | NAPONICR | PM - Preventative Maintenance | 2022-11-16 | 2022-11-27
77462271 | 1018214050 | DEMATIC MODEL 9265 13 WEEK PM | DGULDIN | PM - Preventative Maintenance | 2022-11-16 | 2022-11-27
77446827 | 1013890000 | Remove double dutchman | FICERIC | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-10-15 | 2022-11-04 | AZJSER
77405579 | 1018214045 | DEMATIC MODEL 9265 13 WEEK PM | DGULDIN | PM - Preventative Maintenance | 2022-11-16 | 2022-11-26
77405576 | 1018214025 | DEMATIC MODEL 2467 13 WEEK PM | DGULDIN | PM - Preventative Maintenance | 2022-11-16 | 2022-11-26
77405571 | 1018214020 | DEMATIC MODEL 9265 13 WEEK PM | DGULDIN | PM - Preventative Maintenance | 2022-11-16 | 2022-11-26
77374060 | 100733255 | DD 119 has a dent near the lower right side | HANEJAM | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-10-13 | 2022-12-12
77371305 | MOD.002 | SOFTLINES MOD LANE 4 IR | LMDURHAM | PdM - Work using a Predictive Tool | 2022-11-16 | 2022-11-17
77371292 | MOD.002 | SOFTLINES MOD LANE 3 IR | LMDURHAM | PdM - Work using a Predictive Tool | 2022-11-16 | 2022-11-17
77371283 | PCK.044 | SOFTLINES PACK LANE1 IR | WANSEDAV | PdM - Work using a Predictive Tool | 2022-11-16 | 2022-11-17
77371253 | PCK.044 | SOFTLINES PACK LANE 5 IR | WANSEDAV | PdM - Work using a Predictive Tool | 2022-11-16 | 2022-11-17
77371246 | PCK.044 | SOFTLINES PACK LANE 4 IR | WANSEDAV | PdM - Work using a Predictive Tool | 2022-11-16 | 2022-11-17
77371232 | PCK.044 | SOFTLINES PACK LANE 2 IR | WANSEDAV | PdM - Work using a Predictive Tool | 2022-11-16 | 2022-11-17
77371223 | PCK.044 | SOFTLINES PACK LANE 6 IR | WANSEDAV | PdM - Work using a Predictive Tool | 2022-11-16 | 2022-11-17
77371205 | PCK.044 | SOFTLINES PACK LANE 7 IR | WANSEDAV | PdM - Work using a Predictive Tool | 2022-11-16 | 2022-11-17
77371196 | PCK.044 | SOFTLINES PACK LANE 3 IR | WANSEDAV | PdM - Work using a Predictive Tool | 2022-11-16 | 2022-11-17
77346635 | 1018213000 | DEMATIC MODEL 9570 3 MONTH PM SCHEDULE | NAPONICR | PM - Preventative Maintenance | 2022-11-12 | 2022-11-25
77346571 | PCK.044 | SOFTLINES PACK LANE 2 AIR LEAK INSPECTION | WANSEDAV | PdM - Work using a Predictive Tool | 2022-11-16 | 2022-11-25
77343768 | AR.BOT.HDU.X16N-N-2035-002503 | X DRIVE BOT 26 WEEK PM | MUBARRET | PM - Preventative Maintenance | 2022-11-16 | 2022-12-04
77343765 | AR.BOT.HDU.X16N-N-2035-002502 | X DRIVE BOT 26 WEEK PM | MUBARRET | PM - Preventative Maintenance | 2022-11-16 | 2022-12-04
77342146 | AR.BOT.HDU.X16N-N-2035-002504 | X DRIVE BOT 52 WEEK PM | MUBARRET | PM - Preventative Maintenance | 2022-11-16 | 2022-12-14
77342142 | AR.BOT.HDU.X16N-N-2035-002505 | X DRIVE BOT 52 WEEK PM | MUBARRET | PM - Preventative Maintenance | 2022-11-16 | 2022-12-14
77141179 | 1018100000 | 'ordered' Sensor Issues | BOARDERR | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-10-08 | 2022-10-29 | ZSINGER
77064456 | SHP.056 | SOFTLINES SHIP LANE 2 OF 2 BEARING US CRITICALITY 2 | ORZMIGUE | PdM - Work using a Predictive Tool | 2022-11-10 | 2022-11-19
77057581 | DEPT.AMCARE.057 | [RDG1] MHW ZEN ROOM/AMCARE DOOR | HANEJAM | Project - Work beyond normal Repair & Maint. | 2022-10-06 | 2022-12-05
77013683 | AUD.EQUP | AUDIT to quantify Pre-Action Systems, FLS Pumps, Water Storage & Elevators | HANEJAM | Audit (General Audit) | 2022-10-31 | 2022-11-18
77004146 | 1018104100 | Moving AME box | DGULDIN | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-10-05 | 2022-12-04 | DGULDIN
76704767 | 1018300030 | DEMATIC MODEL 2430-SL2 SORTER 13 WEEK PM | DGULDIN | PM - Preventative Maintenance | 2022-11-02 | 2022-11-11
76495431 | CART.GC | Red Tag Area Pick Cart cleanup | ZSINGER | Project - Work beyond normal Repair & Maint. | 2022-09-23 | 2022-11-22 | MATHEAST
76463964 | G.ELEC.LIGHT.PARK.242 | Lights in yard that are out. | HANEJAM | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-09-22 | 2022-11-21
76319061 | 1013850630 | remove links | ERNSW | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-10-13 | 2022-11-17 | ADCOURTR
75462853 | 1018890020 | 'ordered' gear box is leaking oil | BOARDERR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-09-30 | 2022-09-20 | ERNSW
75352576 | 1018680000 | Pack Line Bulk takeaway Signage | NUTTERGN | Project - Work beyond normal Repair & Maint. | 2022-08-27 | 2022-10-26
74916537 | BLDG.FLS.MONITORING | BMS Alarm - FP_01 serving [Equip Serves] systemTrouble | HANEJAM | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-08-17 | 2022-09-06
74909762 | 1013223095 | Motor and Gearbox Misaligned Causing Belt Damage | SEIGELJS | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-11-15 | 2022-10-15 | CODREICH
74396095 | 1018104330 | Guide bearing need adjustment | BENJACOH | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-10-28 | 2022-10-02 | ORZMIGUE
73857685 | 1018400025 | extreme wear and cracks on v belt | ADCOURTR | Corrective - Not running at 100%, can be scheduled, and not found on a checklist | 2022-08-03 | 2022-09-17 | WANSEDAV
72489750 | FLS.SPKLR.049 | !Sprinkler system deficiencies | KUPETZTJ | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-06-16 | 2022-07-07 | HANEJAM
71935474 | MOD.002 | 2022 E-Stop Cover Replacements | BOARDERR | Project - Work beyond normal Repair & Maint. | 2022-06-02 | 2022-08-01 | BOARDERR
69076634 | AR.BOT.HDU.X16N-N-2035-002244 | Drive will not in service | ADCOURTR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | 2022-09-07 | 2022-05-27 | KARCHERC
66178634 | GNRL.075 | 2022 Part Rebuild and Belt Cutting | BOARDERR | Project - Work beyond normal Repair & Maint. | 2022-01-19 | 2022-03-20 | TONYBENZ

## Follow Ups
Work Order | Equipment | Description | 1 - WO Owner | Type | Reported By
78891883 | 1018500055 | pin replacement/clicking snubber (Charge end) | ADCOURTR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | ADCOURTR
78886970 | 1018221070 | AR FLOOR CHUTE LUBRICATION | MOTRONIM | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | MOTRONIM
78878876 | RDG1.SLAM.06 | Monitor SLAMs | MLLERHB | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | MLLERHB
78869743 | 1018300030 | V groove wheel replacement | BOARDERR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | DGULDIN
78826570 | 1018231130 | Drive belt needs alignment | ZSINGER | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | JERNUTTE
78826039 | 1018233135 | drive pulleys need to be aligned | ZSINGER | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | JERNUTTE
78821996 | 1018300050 | 'kitted' BROKEN FINGER GUARDS | KUPETZTJ | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | KRISHBTY
78821854 | 1018300045 | 'ordered' BROKEN FINGER GUARD | BOARDERR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | KRISHBTY
78810339 | 1018500350 | 'ordered' end roller shaft/bearing completely worn out | BOARDERR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | WANSEDAV
78790526 | 1018223015 | replace main belt pin | FICERIC | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | ADCOURTR
78729723 | 10SL0312 | Slam 3 Strip Belt Worn/missing/damaged belts | BENJACOH | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | BENJACOH
78727464 | 1013500436 | Belt L on 500436 in need of replacement | ERNSW | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | NHUBJERE
78727408 | 1013500435 | 'kitted' Multiple belts found in need of replacement | KUPETZTJ | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | NHUBJERE
78661126 | 1018430820 | BEARING IS SHOT. AXLE IS SPINNING INSIDE THE ROLLER. 430700 | SAMBADRA | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | MOTRONIM
78659408 | 1018500865 | bad discharge end roller. It's red tagged and noisy. see pic | SAMBADRA | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | MOTRONIM
78629683 | 1013800560 | oil leak gear box | TROUGHTI | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | TROUGHTI
78629067 | 1013800000 | belt hoping looks like damaged pully is the cause | SAMBADRA | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | TROUGHTI
78628855 | 1013800020 | light oil leak | TROUGHTI | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | TROUGHTI
78604457 | 1018500865 | 'kitted' 500865 bed "F" near the top of the incline. belt is hitting bed. | KUPETZTJ | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | MOTRONIM
78584514 | 1018600015 | PIN IS RUSTY ON SLAVE BED. THE LACING IS ETCHING IN TO IT. | TROUGHTI | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | MOTRONIM
78582855 | 1018500835 | lacing is sticking upward on bed F on 500835 | SAMBADRA | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | MOTRONIM
78549830 | 1018890130 | gearbox hanging from incline is 133 degrees. | KUPETZTJ | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | WANSEDAV
78516468 | 1018108000 | 'ordered' SHAFT FAILING | BOARDERR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | KRISHBTY
78456642 | SHP.056 | missaligned drive sheaves | TROUGHTI | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | SKEIDERL
78454994 | 1018430000 | 'ordered' REPLACE ROLLERS | BOARDERR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | KRISHBTY
78416589 | 1018300095 | V belt damage. Needs to be replaced. | SAMBADRA | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | MOTRONIM
78403250 | 1018500855 | 'kitted' BAD MDR 500855. LAST CURVED BED. | KUPETZTJ | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | MOTRONIM
78385382 | CNTRL.080 | Spare Compact logix PLC processor firmware update | PTHR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | PTHR
78375936 | 1018500835 | 'ordered' bad roller on bed E. Marked with an "X". | TONYBENZ | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | MOTRONIM
78354508 | BLDG.DOCK | Finish Dock door quarterly PM | HANEJAM | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | HANEJAM
78343507 | 1018300013 | 300013 Brake Meter Drive Alignment | ERNSW | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | BENJACOH
78342267 | 1018500765 | 'ordered' Bad discharge end roller. BED E | BOARDERR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | MOTRONIM
78271691 | 10SL0313 | *Kitted* There were large holes in BOTH (two belts needed) conical belts | BENJACOH | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | NHUBJERE
78232824 | 1018700000 | 'kitted' v belt has at least one crack and appears to be delaminating | KUPETZTJ | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | WANSEDAV
78204398 | 1018890130 | take up roller making loud clicking noise | BOARDERR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | WANSEDAV
78165163 | 1013850530 | drive pulleys missaligned bed number 1018850530 | MOTRONIM | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | SKEIDERL
78086654 | DEPT.OB.057 | Bollards need to be installed at DD149 | HANEJAM | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | BENJACOH
77934047 | 1013800500 | *Kitted* Gearbox is leaking from rear seal | CODREICH | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | ERNSW
77890672 | 1018300030 | ticking noise (see comments) | DGULDIN | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | LMDURHAM
76319061 | 1013850630 | remove links | ERNSW | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | ADCOURTR
76318918 | 1013850110 | remove links | HILLMROB | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | ADCOURTR
75748442 | 1013850020 | *Kitted* clicking sound emanating from output bearing of gearbox | DGULDIN | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | PEKARIKC
75462853 | 1018890020 | 'ordered' gear box is leaking oil | BOARDERR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | ERNSW
74909762 | 1013223095 | Motor and Gearbox Misaligned Causing Belt Damage | SEIGELJS | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | CODREICH
74556833 | 1013800160 | *kitted* gearbox leaking | CODREICH | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | PEKARIKC
74396095 | 1018104330 | Guide bearing need adjustment | BENJACOH | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | ORZMIGUE
72489750 | FLS.SPKLR.049 | !Sprinkler system deficiencies | KUPETZTJ | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | HANEJAM
71254295 | 1013800045 | 1 missing roller on the underside. | DGULDIN | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | ADCOURTR
69076634 | AR.BOT.HDU.X16N-N-2035-002244 | Drive will not in service | ADCOURTR | Follow-Up - Comes from a scheduled WO Checklist (PM, PdM) | KARCHERC

## Training
Work Order | Description | 1 - WO Owner
78884880 | RME- EQP MONTHLY TECH DRILL TRAINING
78743793 | RME- EQP WEEKLY TRAINING (KNET/JQS/SAFETY)
78743699 | AE TEAM TRAINING (KNET/JQS/SAFETY/TECH DRILL) WEEKLY
78632998 | AE TEAM TRAINING (KNET/JQS/SAFETY/TECH DRILL) WEEKLY
78573486 | RME- CONTROLS MONTHLY TECH DRILL
78432047 | RME- EQP WEEKLY TRAINING (KNET/JQS/SAFETY) | KUPETZTJ
78432031 | AE TEAM TRAINING (KNET/JQS/SAFETY/TECH DRILL) WEEKLY | KUPETZTJ
78324214 | AE TEAM TRAINING (KNET/JQS/SAFETY/TECH DRILL) WEEKLY | KUPETZTJ
78144315 | AE TEAM TRAINING (KNET/JQS/SAFETY/TECH DRILL) WEEKLY | KUPETZTJ
78144265 | RME- EQP WEEKLY TRAINING (KNET/JQS/SAFETY) | KUPETZTJ
78009582 | AE TEAM TRAINING (KNET/JQS/SAFETY/TECH DRILL) WEEKLY | KUPETZTJ
77820705 | RME- EQP WEEKLY TRAINING (KNET/JQS/SAFETY) | KUPETZTJ
77820697 | AE TEAM TRAINING (KNET/JQS/SAFETY/TECH DRILL) WEEKLY | KUPETZTJ
77714797 | AE TEAM TRAINING (KNET/JQS/SAFETY/TECH DRILL) WEEKLY | KUPETZTJ
77576129 | RME- EQP MONTHLY TECH DRILL TRAINING | GENSHART
77541249 | RME- EQP WEEKLY TRAINING (KNET/JQS/SAFETY) | KUPETZTJ
77541242 | AE TEAM TRAINING (KNET/JQS/SAFETY/TECH DRILL) WEEKLY | KUPETZTJ
77424179 | AE TEAM TRAINING (KNET/JQS/SAFETY/TECH DRILL) WEEKLY | KUPETZTJ
77228631 | RME- CONTROLS MONTHLY TECH DRILL | GENSHART
77192469 | RME- EQP WEEKLY TRAINING (KNET/JQS/SAFETY) | KUPETZTJ
77192459 | AE TEAM TRAINING (KNET/JQS/SAFETY/TECH DRILL) WEEKLY | KUPETZTJ
76236100 | RME- EQP MONTHLY TECH DRILL TRAINING | GENSHART
75954713 | RME- CONTROLS MONTHLY TECH DRILL | GENSHART
75678090 | AMAZON AWCS TRAINING | GENSHART